## Gantt Chart & Schedule
Minimum-Disruption Security Containment Framework — 7-Week Project Timeline
Implementation Roadmap & Visual Gantt Chart covering core features, simulator, graph engine, optimiser, dashboard, and evaluation.
ID | Phase / Task Description | 7-Week Schedule Timeline
|  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7
P1 | Phase 1: Architecture & Data Schema
1.1 | Define JSON Event Schema (#3) & REST API Spec (#45)
1.2 | Design Dynamic Capability Graph Data Structures (#6)
P2 | Phase 2: Simulator & Event Ingestion Engine
2.1 | Build Multi-Agent Simulator with Scripted Agents (#1)
2.2 | Implement Event Collector (#4) & Context Classifier (#5)
2.3 | Setup Agent Activity Audit History Logging (#31)
P3 | Phase 3: Security Risk Detector & Enforcement
3.1 | Build Policy Engine (#8) & Path-Finding Risk Detector (#9)
3.2 | Assign Risk/Severity Levels (#11)
3.3 | Develop Enforcement Engine & Edge Blockers (#16, #24)
P4 | Phase 4: Disruption Optimiser & Baselines
4.1 | Develop Disruption Cost Model (#14) & Min-Cut Optimiser (#15)
4.2 | Implement Baseline A (Shutdown #36) & Baseline B (Static Cut #37)
4.3 | Implement Baseline C (Adaptive Containment #38)
P5 | Phase 5: Operator Security Dashboard
5.1 | Develop Security Dashboard Overview Page (#26)
5.2 | Build Interactive Live Capability Graph Page (#27) (replays simulator runs, not live monitoring)
5.3 | Construct Auditable Incident Detail Page (#28)
P6 | Phase 6: Benchmark Scenarios & Evaluation
6.1 | Finalize Multi-Agent Attack & Benign Scenario Dataset (#35)
6.2 | Run Benchmarks & Collect Security Effectiveness Metrics (#39)
6.3 | Calculate Operational Disruption (#40) & Latency Metrics (#43) (runs, but has no tests)
P7 | Phase 7: System Integration & Documentation
7.1 | End-to-End Integration Testing across Simulator & API
7.2 | Code Cleanup, Package Containerization & API Docs
7.3 | Synthesize Results & Submit Final Research Thesis
Key Project Deliverable Milestones
M1 | Core API Specification & Graph Engine Schema Finalized
M2 | Multi-Agent Simulator Ingesting Events into Dynamic Graph
M3 | Runtime Risk Detector & Enforcement Engine Operational
M4 | Min-Disruption Optimiser & Baselines A/B/C Implemented
M5 | Interactive Security Operator Dashboard Deployed
M6 | Benchmark Evaluation Complete (Effectiveness & Disruption Data Captured)
M7 | Final Integrated Prototype, Thesis & API Package Delivered